## OriginalPlan
Dates: | 2017-10-19 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23
Nottingham University | [10 empty] | Holiday |  |  |  | Exams | [8 empty] | Holiday | [5 empty] | Christmas Holiday - 15/12 - 15/1
Local Primary Schools | [10 empty] | Holiday | [13 empty] | Holiday |  |  |  |  | Exams - 15/1 - 27/1
Tasks: | [29 empty] | Primary School holiday - 22/12 - 8/1
General Research
School contact
Equipment Gathering
Ethics and Proposal
New Website
Update Original Games | [29 empty] | Tasks
Improved Stat. Tracking
Add New Games
Secure Login Account System
Teacher/Admin portal
Improved Strat Tracking for Data Analysis (Mouse tracking, response times etc.)
Game testing
Interim Report
Word recognition M.L
Specialised word selection M.L
Machine Learning Testing | [29 empty] | Git/Server
User Testing
Data Analysis | [29 empty] | AI - Machine Learning….
Presentation of data | [29 empty] | Contact Local Authority for Sponsorship
Acceptance Testing
Data Analysis
| Bottlenecks | [28 empty] | Report editing and finalisation
| Schools | [28 empty] | Pre-User Testing
| Ethics | [28 empty] | Acceptance Testing
Shared Courseworks

## ActualWork
Dates: | 2017-10-19 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23
Nottingham University | [10 empty] | Holiday |  |  |  | Exams | [8 empty] | Holiday | [5 empty] | Christmas Holiday - 15/12 - 15/1
Local Primary Schools | [10 empty] | Holiday | [13 empty] | Holiday |  |  |  |  | Exams - 15/1 - 27/1
Tasks: | [29 empty] | Primary School holiday - 22/12 - 8/1
General Research
School and Council contact
Equipment Gathering
Ethics and Proposal
New Website
Update Original Games | [29 empty] | Tasks
Improved Stat. Tracking
Add New Games
Secure Login Account System
Teacher/Admin portal
Multiplayer Tasks
User Avatars | [29 empty] | Improved Strat Tracking for Data Analysis (Mouse tracking, response times etc.)
Game testing
Interim Report
Word recognition M.L
Specialised word selection M.L
Machine Learning Testing | [29 empty] | Git/Server
User Testing
Data Analysis | [29 empty] | AI - Machine Learning….
Presentation of data | [29 empty] | Contact Local Authority for Sponsorship
Acceptance Testing
Data Analysis
| Bottlenecks | [28 empty] | Report editing and finalisation
| Schools | [28 empty] | Pre-User Testing
| Ethics | [28 empty] | Acceptance Testing
Shared Courseworks

## Sheet2
Reading
% Working at Expected Standard | 51
% Working at Greater Depth | 25
% Not Reaching Expected Standard | 24
Writing
% Working at Expected Standard | 52
% Working at Greater Depth | 16
% Not Reaching Expected Standard | 32